## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-07-B-MM
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a user, I want to see a log in page so that I can type in my username to get access to the dashboard and my user-specific permissions. | GIVEN the server is up, WHEN I enter the website name, THEN expect log-in page. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am trying to log in, WHEN I attempt to access logging in with an incorrect username, THEN I expect to be denied access and receive an appropriate error message. | Pass | EK, 3/28/24 3:00 PM
| GIVEN certain username is already part of the database, WHEN I enter said username into the login page THEN I expect to be taken to dashboard. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am logged in as a user, WHEN I click the logout button, THEN I expect to be redirected to the login page and for my session storage to be cleared | Pass | EK, 3/28/24 3:00 PM
As a Helper I want to add/remove a scheme to my evil basket so that I can proceed to checkout. | GIVEN list of schemes WHEN I add scheme to evil cart THEN I expect that scheme in evil cart. | Pass | EK, 3/28/24 3:00 PM
| GIVEN list of schemes in evil cart WHEN I remove scheme from evil cart THEN I expect that scheme in evil cart to be removed. | Pass | EK, 3/28/24 3:00 PM
As a developer I want ways to display buttons based on the current user’s permissions so that users will be able to do actions specific to them. | GIVEN I am logged in as a user WHEN I look into the session storage THEN I see my username and role. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am logged in as a user WHEN I look at the profile (top right) THEN I see my username and role. | Pass | EK, 3/28/24 3:00 PM
As a Helper I want to be able to search through the available schemes so that I don't have to look through the whole list to see one I want to fund. | Given there are schemes displayed when a user types in a title or name, then I expect to be able to see keywords related to the scheme/villain I am looking for, and I expect a list of schemes updated as I type, containing the typed keywords to be displayed. | Pass | EK, 3/28/24 3:00 PM
| Given a user enters a scheme or villain name that does not exist, I expect "no result" to be returned as a keyword from search bar displayed. | Pass | EK, 3/28/24 3:00 PM
As a Helper I want to look at all different villain schemes so that I can choose which ones to contribute to. | GIVEN I pass the log in WHEN I enter the dashboard THEN a list of all villain schemes should be displayed | Pass | EK, 3/28/24 3:00 PM
As a Helper I want to check out my evil basket so that I can fund all the schemes I’ve chosen. | Given SCHEMES IN EVIL CART when I CHECKOUT then I EXPECT CHECKOUT TO BE PROCESSED | Pass | EK, 3/28/24 3:00 PM
As a Manager, I want to be able to put the villain’s schemes on the website, so that they can be funded. | Given THERE IS SCHEME when I LOG IN AS ADMIN then I AM ABLE TO ADD OR REMOVE SCHEMES. | Pass | EK, 3/28/24 3:00 PM
As a Villain, I want to efficiently manage my schemes on the website, so I can track my progress and optimize my evil plans. | Given when I log in as a Villain when I search up my name or scheme, then I expect see a list of all my schemes with my details such as name, description, funding goal, and current funding progress. | Pass | EK, 3/28/24 3:00 PM
As a user, I want to be able to customize my profile picture so that others can see who I am. | GIVEN there is a user with an imgUrl in users.json that is associated with an image in data/pictures, WHEN I log in as that user THEN I expect to see that user's associated picture in the top right. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am logged in as any user WHEN I click on my name in the top right THEN I expect to see my profile page with all of my information from users.json. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am the same user as the profile WHEN I choose a file and press upload THEN I expect my pictures to update instantly and for my imgUrl to change in users.json. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am the same user as the profile WHEN I upload a picture that isn't square THEN I expect to be shown a square image cropped from the center. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am on a scheme-detail page and the villain who posted the scheme is in users.json WHEN I click on their name THEN I expect to be taken to their profile. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am logged in as any user WHEN I am on a profile that is not my own THEN I expect not to be able to edit that user's picture. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am logged in as any user WHEN I am on a profile that is not my own and I click my profile link THEN I expect for the profile page to update to by information. | Pass | EK, 3/28/24 3:00 PM
As a user, I want to be able to write out a backstory, a set of goals, and my achievements so others know who I am. | GIVEN I am the same user as the profile WHEN I type in the description box, add/remove/edit achievements, and then press save changes, THEN I expect my changes to be written into description and achievements in users.json. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am the same user as the profile & there are 0 to many achievements WHEN I press add new achievement, THEN I should expect to see an empty field to type in. | Pass | EK, 3/28/24 3:00 PM
| GIVEN I am logged in as any user WHEN I am on a profile that is not my own THEN I expect not to be able to edit that user's information. | Pass | EK, 3/28/24 3:00 PM