## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-07-B-MM
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a user, I want to see a log in page so that I can type in my username to get access to the dashboard and my user-specific permissions. | GIVEN the server is up, WHEN I enter the website name, THEN expect log-in page. | Pass | EK, 3/16/24
| GIVEN I am trying to log in, WHEN I attempt to access logging in with an incorrect username, THEN I expect to be denied access and receive an appropriate error message. | Pass | EK, 3/16/24
| GIVEN certain username is already part of the database, WHEN I enter said username into the login page THEN I expect to be taken to dashboard and my data to be stored in session storage | Pass | EK, 3/16/24
| GIVEN I am logged in as a user, WHEN I click the logout button, THEN I expect to be redirected to the login page and for my session storage to be cleared | Pass | EK, 3/16/24
As a Helper I want to add/remove a scheme to my evil basket so that I can proceed to checkout. | GIVEN list of schemes WHEN I add scheme to evil cart THEN I expect that scheme in evil cart. | Pass | JC, 3/19/24
| GIVEN list of schemes in evil cart WHEN I remove scheme from evil cart THEN I expect that scheme in evil cart to be removed. | Pass | JC, 3/19/24